## Sheet1
Description | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16 | Who? | Extended description
MAJOR BUILDS / MILESTONES
Abalon Game
AI
Advanced AI
Researching general AI approach | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16
Alpha Beta heuristic on monte carlo tree | [6 empty] | Loris + Clement + Ivan
Simulated annealing | [6 empty] | Mathias + Aaron
Genetic algorithms | [6 empty] | Adele + Guillaume
ML/DL | [6 empty] | Mathias + Ivan
AI Application (evaluation function, etc) | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16
Alpha Beta heuristic on monte carlo tree | [6 empty] | TODO | as soon as general approaches are determined
Simulated annealing | [6 empty] | TODO
Genetic algorithms | [6 empty] | TODO
ML/DL | [6 empty] | TODO
TODO
Game mechanic | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16
UML + initialization | [6 empty] | All | In progress, established main components
Move correctness checker | [6 empty] | Mathias + Loris
Selection method | [6 empty] | Mathias + Loris
Move method (board update, etc) | [6 empty] | Mathias + Loris
Mouse listener for selection | [6 empty] | Ivan
Converter from global coordinates to local coordinates | [6 empty] | Ivan
Selection processer | [6 empty] | Ivan
GUI | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16
Menu bar / Menu GUI | [6 empty] | Clement + Guillaume
Move GUI ideas | [6 empty] | All
Move GUI implementation | [6 empty] | Clement + Guillaume
GUI library research | [6 empty] | Aaron + Adele + Ivan | Found out that JavaFX contains all the needed components
GUI bug fix | [6 empty] | Aaron + Adele + Ivan
Advanced Graphics | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-10 | 2020-10-16
Marbles regular graphics | [6 empty] | Aaron + Adele + Ivan
Board regular graphics | [6 empty] | Aaron + Adele + Ivan
Marbles hovering | [6 empty] | Aaron + Adele + Ivan
Marbles selection | [6 empty] | Aaron + Adele + Ivan
Board hovering | [6 empty] | Aaron + Adele + Ivan
Board selection | [6 empty] | Aaron + Adele + Ivan
Move animation with threads | [6 empty] | Ivan
Convenient duration (Soft deadline)
Acceptable duration (Strict deadline)
Disaster
Done