## Sheet1
Description | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | Who? | Extended description
MAJOR BUILDS / MILESTONES
Abalon Game
Researching general AI approach
Ideas
Simulated annealing
Genetic algorithms
ML/DL
BOTS/AI
Game Tree Data Structure
Find every possible moves | [7 empty] | Mathias - Aaron - Ivan
Evaluation Function | [7 empty] | Everyone
Monte Carlo Tree Search | [7 empty] | Mathias - Aaron - Ivan - Guillaume
Research
Implementation Data Structure
Implementation of strategy
Complexity analysis
Mini-Max Algorithm (+ Alpha Beta) | [7 empty] | Clement - Adele - Loris - Ivan
Research
Implementation Data Structure
Implementation of strategy
Complexity analysis
Naive Bot | [7 empty] | (first team to finish its bot)
Research
Implementation
GUI | [7 empty] | If we have time, second team to finsih their bot
Improve Game play
Change Board looking
Change marbles
Improve Menu
Music
Effects (Game Over..)
TEST | [7 empty] | Everyone
Compare different AI's
Test
PHASE 1
Game mechanic
UML + initialization | [7 empty] | All | In progress, established main components
Move correctness checker | [7 empty] | Mathias + Loris
Selection method | [7 empty] | Mathias + Loris
Move method (board update, etc) | [7 empty] | Mathias + Loris
Mouse listener for selection | [7 empty] | Ivan
Converter from global coordinates to local coordinates | [7 empty] | Ivan
Selection processer | [7 empty] | Ivan
GUI
Menu bar / Menu GUI | [7 empty] | Clement + Guillaume
Move GUI ideas | [7 empty] | All
Move GUI implementation | [7 empty] | Clement + Guillaume
GUI library research | [7 empty] | Aaron + Adele + Ivan | Found out that JavaFX contains all the needed components
GUI bug fix | [7 empty] | Aaron + Adele + Ivan
Advanced Graphics | 13.09 | 20.09 | 27.09 | 04.10 | 10.10 | 16.10
Marbles regular graphics | [7 empty] | Aaron + Adele + Ivan
Board regular graphics | [7 empty] | Aaron + Adele + Ivan
Marbles hovering | [7 empty] | Aaron + Adele + Ivan
Marbles selection | [7 empty] | Aaron + Adele + Ivan
Board hovering | [7 empty] | Aaron + Adele + Ivan
Board selection | [7 empty] | Aaron + Adele + Ivan
Move animation with threads | [7 empty] | Ivan
Suppose to be done