## Sheet1
Description | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | Who? | Extended description
MAJOR BUILDS / MILESTONES
Abalon Game
Researching general AI approach
Ideas
Simulated annealing (discard)
Genetic algorithms (discard)
ML/DL (discard)
BOTS/AI
Game Tree Data Structure | [7 empty] | Aaron Adele Clement
Find every possible moves | [7 empty] | Mathias
Evaluation Function | [7 empty] | Clement
Monte Carlo Tree Search | [7 empty] | Mathias - Aaron - Clement - Guillaume
Research | [7 empty] | Clement
Implementation Data Structure | [7 empty] | Aaron - Guillaume
Implementation of strategy - Optimizing | [7 empty] | Mathias
Complexity analysis | [7 empty] | Everyone from this section
Mini-Max Algorithm (+ Alpha Beta) | [7 empty] | Clement - Adele - Loris - Ivan
Research | [7 empty] | Clement
Implementation Data Structure | [7 empty] | Loris
Implementation of strategy - Optimization | [7 empty] | Clement - Adele
Complexity analysis | [7 empty] | Everyone from this section
Naive Bot | [7 empty] | Guillaume
Research | [7 empty] | Guillaume
Implementation | [7 empty] | Guillaume
GUI | [7 empty] | If we have time, second team to finsih their bot
Improve Game play | [7 empty] | Ivan
Change Board looking | [7 empty] | optional
Change marbles | [7 empty] | optional
Improve Menu | [7 empty] | optional
Music | [7 empty] | Aaron
Effects (Game Over..) | [7 empty] | Aaron
TEST | [7 empty] | Everyone
Compare different AI's | [7 empty] | Clement
Test | [7 empty] | Loris
Presentation | [7 empty] | Everyone
Report | [7 empty] | Everyone
Introduction | [7 empty] | Adele
Abstract | [7 empty] | Adele
Draft | [7 empty] | Adele
PHASE 1
Game mechanic
UML + initialization | [7 empty] | All | In progress, established main components
Move correctness checker | [7 empty] | Mathias + Loris
Selection method | [7 empty] | Mathias + Loris
Move method (board update, etc) | [7 empty] | Mathias + Loris
Mouse listener for selection | [7 empty] | Ivan
Converter from global coordinates to local coordinates | [7 empty] | Ivan
Selection processer | [7 empty] | Ivan
GUI
Menu bar / Menu GUI | [7 empty] | Clement + Guillaume
Move GUI ideas | [7 empty] | All
Move GUI implementation | [7 empty] | Clement + Guillaume
GUI library research | [7 empty] | Aaron + Adele + Ivan | Found out that JavaFX contains all the needed components
GUI bug fix | [7 empty] | Aaron + Adele + Ivan
Advanced Graphics | 13.09 | 20.09 | 27.09 | 04.10 | 10.10 | 16.10
Marbles regular graphics | [7 empty] | Aaron + Adele + Ivan
Board regular graphics | [7 empty] | Aaron + Adele + Ivan
Marbles hovering | [7 empty] | Aaron + Adele + Ivan
Marbles selection | [7 empty] | Aaron + Adele + Ivan
Board hovering | [7 empty] | Aaron + Adele + Ivan
Board selection | [7 empty] | Aaron + Adele + Ivan
Move animation with threads | [7 empty] | Ivan
Suppose to be done