## Sheet1
Description | Who? | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-11 | 2020-10-18 | Extended description
MAJOR BUILDS / MILESTONES
Abalon Game
AI
Advanced AI
Report
Looking for ideas for the research that could be done with AI | All
Bot
Research on AI techniques for phases 2 & 3 | All
Game mechanic
UML + initialization | All | [7 empty] | In progress, established main components
Game Engine (processes the game following the rules) | Mathias + Loris + Adele
Player Move listener: marbles selection | Aaron + Ivan
Player Move listener: marbles motion | Clement + Guillaume
GUI
Menu bar / Menu GUI | Clement + Guillaume
Move GUI | Mathias + Loris
GUI library research | Aaron + Adele + Ivan
Advanced Graphics
Marbles regular graphics | Aaron + Adele + Ivan
Board regular graphics | Guillaume + Clement
Marbles hovering | Aaron + Adele + Ivan
Marbles selection | Aaron + Adele + Ivan
Board hovering | Guillaume + Clement
Board selection | Guillaume + Clement
Planned convinient duration
Finished earlier than planned
Critically behind on schedule
Acceptable duration
Disaster
Have something ready, even tough it's not optimal
Slightly behind
Requires extra attention